## Feature Inventory
QEP Phase | IntelliDealer Module | Feature / Screen | IntelliDealer Menu Path | PDF Evidence | Screenshot Count | Data Source | Security Switch | QEP OS Coverage Status | Notes / Gap
Phase 1 — Core CRM | Financial Management | Customer Profile: Search and Listing | IntelliDealer Menus > Financial Management > Accounts Receivable > Customer Profile: Listing | Customer Profile: Search and Listing.pdf | 2 | CMASTR |  | IN BUILD (Sprint 2) | Company & Contact Management module — company-first, not contact-first
Phase 1 — Core CRM | Financial Management | Customer Reports | IntelliDealer Menus > Financial Management > Accounts Receivable > Customer | Customer Reports.pdf | 0 |  |  | PLANNED (Phase 9) | Advanced BI + customer portal reports
Phase 1 — Core CRM | Product Support | Prospect Board | IntelliDealer Menus > Product Support > Equipment Product Support > Prospect Board | Prospect Board.pdf | 3 |  |  | IN BUILD (Sprint 3) | Deal Pipeline — Kanban, replaces Prospect Board
Phase 1 — Core CRM |  | Customer Profile (Contacts) |  |  | 2 |  |  | IN BUILD (Sprint 2) | Company & Contact Management module — company-first, not contact-first
Phase 1 — Core CRM |  | Customer Profile (Details) |  |  | 1 |  |  | IN BUILD (Sprint 2) | Company & Contact Management module — company-first, not contact-first
Phase 1 — Core CRM |  | Customer Profile (Notes) |  |  | 1 |  |  | IN BUILD (Sprint 2) | Company & Contact Management module — company-first, not contact-first
Phase 1 — Core CRM |  | Customer Profile (Supplement Shipping) |  |  | 1 |  |  | IN BUILD (Sprint 2) | Company & Contact Management module — company-first, not contact-first
Phase 2 — Sales Intelligence | Product Support | Base & Options | IntelliDealer Menus > Product Support > Equipment Product Support > Base & Options: | Base & Options.pdf | 0 |  |  | PLANNED (Phase 2) | Config options for equipment quotes
Phase 2 — Sales Intelligence | Product Support | Equipment Invoicing (Sales Support Portal) | IntelliDealer Menus > Product Support > Equipment Product Support > Equipment Invoicing: Listing | Equipment Invoicing (Sales Support Portal).pdf | 12 | CGIINH |  | PLANNED (Phase 2) | Sales rep workflow replacement
Phase 2 — Sales Intelligence | Product Support | Equipment Listing | IntelliDealer Menus > Product Support > Equipment Product Support > Equipment Profile: | Equipment Listing.pdf | 7 |  |  | PLANNED (Phase 2) | Equipment registry under Company + Deal
Phase 2 — Sales Intelligence | Product Support | Equipment Quoting | IntelliDealer Menus > Product Support > Equipment Product Support > Equipment | Equipment Quoting.pdf | 9 |  |  | BUILT — NEEDS PARITY | QEP Quote Builder live; verify parity against Equipment Quoting + Base & Options
Phase 2 — Sales Intelligence | Product Support | Sales Support Portal | IntelliDealer Menus > Product Support > Equipment Product Support > Sales Support Portal | Sales Support Portal.pdf | 3 |  |  | PLANNED (Phase 2) | Sales rep workflow replacement
Phase 2 — Sales Intelligence |  | Equipment Profile |  |  | 10 |  |  | PLANNED (Phase 2) | Equipment registry under Company + Deal
Phase 2 — Sales Intelligence |  | Equipment Invoicing (Trade Ins) |  |  | 2 |  |  | PLANNED (Phase 8) | Financial Operations: invoicing
Phase 3 — Parts Department | Product Support | Parts Invoicing | IntelliDealer Menus > Product Support > Parts Product Support > Parts Invoicing | Parts Invoicing.pdf | 8 |  |  | PLANNED (Phase 3) | Parts POS + invoicing
Phase 3 — Parts Department | Product Support | Parts Ordering | IntelliDealer Menus > Product Support > Parts Product Support > Parts Ordering | Parts Ordering.pdf | 2 |  |  | PLANNED (Phase 3) | Parts ordering workflow + vendor PO
Phase 3 — Parts Department | Product Support | Parts Profile: Listing | IntelliDealer Menus > Product Support > Parts Product Support > Parts Profile: Listing | Parts Profile: Listing.pdf | 2 |  |  | PLANNED (Phase 3) | Parts inventory master
Phase 3 — Parts Department | Product Support | Price Matrix | IntelliDealer Menus > Product Support > Parts Product Support > Price Matrix | Price Matrix.pdf | 2 |  |  | PLANNED (Phase 3) | Tiered parts pricing
Phase 3 — Parts Department | Financial Management | Purchase Orders | IntelliDealer Menus > Financial Management > Accounts Payable > Purchase Orders | Purchase Orders.pdf | 3 |  |  | PLANNED (Phase 3) | Parts ordering workflow + vendor PO
Phase 3 — Parts Department |  | Parts Quoting (Service) |  |  | 4 |  |  | PLANNED (Phase 3/4) | Parts quoting tied to service/sales
Phase 3 — Parts Department |  | Parts Quoting |  |  | 2 |  |  | PLANNED (Phase 3/4) | Parts quoting tied to service/sales
Phase 4 — Service Department | (multiple) | ID InspectionPlus | IntelliDealer Menus > ID InspectionPlus ID InspectionPlus | ID InspectionPlus.pdf | 1 |  | 923 - ID | PLANNED (Phase 4) | ID InspectionPlus replacement
Phase 4 — Service Department | Product Support | IntelliTech Scheduled Work Orders | IntelliDealer Menus > Product Support > Service Product Support > IntelliTech Scheduled Work Orders | IntelliTech Scheduled Work Orders.pdf | 3 |  |  | PLANNED (Phase 4) | Service work order management
Phase 4 — Service Department | Product Support | Labor Pricing | IntelliDealer Menus > Product Support > Service Product Support > Labor Pricing | Labor Pricing.pdf | 3 |  |  | PLANNED (Phase 4) | Service labor rates
Phase 4 — Service Department | Product Support | Service Agreements (Product Support Quick Links) | IntelliDealer Menus > Product Support > Equipment Product Support > Service | Service Agreements (Product Support Quick Links).pdf | 1 |  |  | PLANNED (Phase 4) | PM contracts + service agreements
Phase 4 — Service Department | Product Support | Technician Service Scheduling | IntelliDealer Menus > Product Support > Service Product Support > Technician | Technician Service Scheduling.pdf | 0 |  |  | PLANNED (Phase 4) | Technician scheduling + dispatch
Phase 4 — Service Department | Product Support | Work Order Quoting:Parts Quoting | IntelliDealer Menus > Product Support > Service Product Support > Work Order | Work Order Quoting:Parts Quoting.pdf | 6 |  |  | PLANNED (Phase 4) | Service work order management
Phase 4 — Service Department | Product Support | Work Orders: Listing | IntelliDealer Menus > Product Support > Service Product Support > Work Order: Listing | Work Orders: Listing.pdf | 3 |  |  | PLANNED (Phase 4) | Service work order management
Phase 4 — Service Department | Product Support | Work in Process | IntelliDealer Menus > Product Support > Service Product Support > Work in Process | Work in Process.pdf | 1 |  |  | PLANNED (Phase 4) | WIP tracking
Phase 4 — Service Department |  | Service Information (Service Technician) |  |  | 1 |  |  | PLANNED (Phase 4) | Technician scheduling + dispatch
Phase 4 — Service Department |  | Service Information |  |  | 1 |  |  | PLANNED (Phase 4) | Service dept scope
Phase 4 — Service Department |  | Work Orders Listing |  |  | 2 |  |  | PLANNED (Phase 4) | Service work order management
Phase 4 — Service Department |  | Work Order Detail |  |  | 1 |  |  | PLANNED (Phase 4) | Service work order management
Phase 4 — Service Department |  | Work Order Detail (Labor/Parts Tabs) |  |  | 1 |  |  | PLANNED (Phase 4) | Service work order management
Phase 4 — Service Department |  | Work Order (Service Parts) |  |  | 1 |  |  | PLANNED (Phase 4) | Service work order management
Phase 4 — Service Department |  | Job Codes |  |  | 1 |  |  | PLANNED (Phase 4) | Job code library
Phase 4 — Service Department |  | Work Order Quoting Listing |  |  | 1 |  |  | PLANNED (Phase 4) | Service work order management
Phase 4 — Service Department |  | Open Work Orders |  |  | 1 |  |  | PLANNED (Phase 4) | Service work order management
Phase 4 — Service Department |  | Open Work Orders Detail |  |  | 1 |  |  | PLANNED (Phase 4) | Service work order management
Phase 5 — Deal Genome (BI) | Management Central | Data Miner | IntelliDealer Menus > Management Central > Utilities > Data Miner | Data Miner.pdf | 0 |  |  | IN PARALLEL BUILD (Phase 5) | Deal Genome engine — 19-page spec delivered; Sprint 1 in pipeline
Phase 5 — Deal Genome (BI) |  | Analysis Reports |  |  | 7 |  |  | IN PARALLEL BUILD (Phase 5) | Deal Genome engine — 19-page spec delivered; Sprint 1 in pipeline
Phase 5 — Deal Genome (BI) |  | Profitability Analysis |  |  | 1 |  |  | IN PARALLEL BUILD (Phase 5) | Deal Genome engine — 19-page spec delivered; Sprint 1 in pipeline
Phase 5 — Deal Genome (BI) |  | Credit Limit Analysis |  |  | 1 |  |  | IN PARALLEL BUILD (Phase 5) | Deal Genome engine — 19-page spec delivered; Sprint 1 in pipeline
Phase 6 — Rental Fleet | Product Support | Rental Counter | IntelliDealer Menus > Product Support > Rental Product Support > Rental Counter | Rental Counter.pdf | 0 |  |  | PLANNED (Phase 6) | Rental fleet management
Phase 8 — Financial Operations | Financial Management | Accounts Payable Outstanding | IntelliDealer Menus > Financial Management > Accounts Payable > A/P Outstanding | Accounts Payable Outstanding.pdf | 2 |  |  | PLANNED (Phase 8) | AP + QuickBooks sync
Phase 8 — Financial Operations | Financial Management | Accounts Receivable - Credit Limit Analysis | IntelliDealer Menus > Financial Management > Accounts Receivable > Credit Limit | Accounts Receivable - Credit Limit Analysis.pdf | 2 |  |  | PLANNED (Phase 8) | AR + QuickBooks export
Phase 8 — Financial Operations | Financial Management | Accounts Receivable - Outstanding A:R | IntelliDealer Menus > Financial Management > Accounts Receivable > A/R | Accounts Receivable - Outstanding A:R.pdf | 2 |  |  | PLANNED (Phase 8) | AR + QuickBooks export
Phase 8 — Financial Operations | Product Support | Billing Analysis | IntelliDealer Menus > Product Support > Service Product Support > Analysis Reports | Billing Analysis.pdf | 0 |  |  | PLANNED (Phase 8) | Real-time billing queue + invoicing
Phase 8 — Financial Operations | Product Support | Customer Pricing | IntelliDealer Menus > Product Support > Parts Product Support > Customer | Customer Pricing.pdf | 1 |  |  | PLANNED (Phase 8) | Customer-specific pricing tier
Phase 8 — Financial Operations | Financial Management | Invoice History Listing | IntelliDealer Menus > Financial Management > Accounts Receivable > Invoice | Invoice History Listing.pdf | 1 |  |  | PLANNED (Phase 8) | Invoice history + archival
Phase 8 — Financial Operations | Financial Management | Real-time Billing Queue | IntelliDealer Menus > Financial Management > Real-time Billing Queue | Real-time Billing Queue.pdf | 4 | BILLINGSCH |  | PLANNED (Phase 8) | Real-time billing queue + invoicing
Phase 8 — Financial Operations |  | Employee Profile (Payroll) |  |  | 1 |  |  | PLANNED (Phase 8/9) | ADP payroll integration
Phase 8 — Financial Operations |  | Employee Profile (Payroll Detail) |  |  | 1 |  |  | PLANNED (Phase 8/9) | ADP payroll integration
Phase 8 — Financial Operations |  | Accounts Receivable (Outstanding Details) |  |  | 1 |  |  | PLANNED (Phase 8) | AR + QuickBooks export
Phase 8 — Financial Operations |  | Invoice History Detail |  |  | 1 |  |  | PLANNED (Phase 8) | Invoice history + archival
Phase 9 — Advanced Intelligence | Customer Care | Customer Portal | IntelliDealer Menus > Customer Care > CRM > Customer Portal | Customer Portal.pdf | 0 |  |  | PLANNED (Phase 9) | External customer portal
Cross-Cutting | Financial Management | Employee Profile | IntelliDealer Menus > Financial Management > Payroll > Employee Profile: Listing | Employee Profile.pdf | 0 |  |  | PLANNED (Phase 8/9) | HR/payroll workflow
Cross-Cutting | Product Support | Traffic Management | IntelliDealer Menus > Product Support > Equipment Product Support > Traffic - | Traffic Management.pdf | 3 |  |  | GAP — SCOPE CHECK | Equipment movement/dispatch tracker not in current roadmap — confirm if needed

## QEP Advantages
Category | QEP OS Capability | What It Does | IntelliDealer Status | Business Impact | QEP Phase | Priority
AI-Native | Knowledge Chat (RAG) | Ask natural-language questions across all QEP docs, SOPs, OEM manuals, bulletins. Returns answers with source citations. | Does not exist. IntelliDealer online help is static HTML search only. | Cuts parts/service lookup time from minutes to seconds. Reduces tribal knowledge dependency on Norman, Bobby, David. | Already Built | HIGH
AI-Native | Voice Capture in Field | Sales rep records customer visit on phone. AI auto-transcribes and extracts deal data (customer, equipment interest, pricing discussed, follow-ups) into QEP CRM. | Does not exist. IntelliDealer requires manual data entry back at the office. | Eliminates the gap between field conversation and CRM entry. David and other reps stop losing deal details between visits. | Already Built | HIGH
AI-Native | AI Call Summarization | Every inbound/outbound call through 8x8 is transcribed, summarized, and attached to the customer record automatically with next-step suggestions. | Does not exist. IntelliDealer has no phone integration. 8x8 operates separately today. | No more "what did we talk about last time" before a callback. Full call history searchable in the CRM. | Phase 1 Sprint 4 | HIGH
AI-Native | AI Receipt & Document Capture | Drop a receipt/invoice PDF or photo into OneDrive. AI extracts vendor, date, amount, line items, and routes to AP for posting. | Does not exist. IntelliDealer AP requires full manual data entry or scanner integration. | Tina gets hours back per week. Fuel receipts and field expenses stop piling up. | Phase 8 | MEDIUM
AI-Native | Voice-to-Quote | Rep says "quote a Yanmar VIO45 with extended warranty for Bob at Acme" — QEP builds the quote draft. | Does not exist. | Reps quote from the truck, not the desk. | Phase 2 | MEDIUM
AI-Native | Deal Genome Engine | 14-variable optimization engine that predicts deal probability, recommends pricing adjustments, and identifies cross-sell opportunities based on customer DNA and fleet profile. | Does not exist. IntelliDealer Data Miner is batch reporting only — no prediction, no optimization. | Turn QEP's historical deal data into a competitive advantage. Quote smarter than Yancey, May Heavy Equipment, Alta. | Phase 5 (parallel) | STRATEGIC
AI-Native | Customer DNA Profiles | Every customer has a profile including fleet composition, seasonal buying patterns, payment behavior, service intensity, communication preferences, and predicted next purchase. | Does not exist. IntelliDealer has Customer Profile with static fields only. | Shift from reactive to predictive sales. Know what Reliable Services needs before they do. | Phase 5 | STRATEGIC
AI-Native | Fleet Prediction | Given a customer's current fleet and industry, predicts what equipment they'll need next and when. | Does not exist. | Proactive outreach beats competitor cold calls. | Phase 5 | HIGH
AI-Native | Market Intelligence Feed | Live FRED economic data, USDA forestry data, IronGuides pricing — integrated into every deal and territory view. | Does not exist. | Price and negotiate with market data at hand. | Phase 5 | MEDIUM
AI-Native | Stalled Deal Alerts | Automated detection when a deal hasn't moved in N days. Suggests specific next action based on deal type. | Does not exist. IntelliDealer Prospect Board is manual. | Deals stop rotting in the pipeline. | Phase 1 Sprint 3 | HIGH
Modern Architecture | Mobile-First Field UX | Every field-facing view (quotes, customer lookup, voice capture, service dispatch) works fully on phone. | IntelliDealer is desktop/green-screen. Reps call the office to run operations from the truck. | Reps run the business from the field. No more "I'll get back to you from the office." | Phase 1+ | HIGH
Modern Architecture | Offline Field Ops | Reps/techs can work offline in poor-signal areas. Auto-syncs when connection returns. | IntelliDealer requires constant connection. | Rural Florida forestry sites — no signal at every tree line. Techs keep working. | Phase 9 | MEDIUM
Modern Architecture | Real-Time Multi-Branch Sync | All branches see the same inventory, deals, and customer records live. | IntelliDealer multi-branch has sync delays and manual reconciliation. | Lake City rep can sell a machine sitting at another branch instantly. | Phase 3 | HIGH
Modern Architecture | Cloud-Native Responsive UI | Modern React/TypeScript, runs on any browser, any device, any OS. | IntelliDealer is legacy desktop. Requires specific client software and desktop setup. | Onboarding new staff is a browser link, not an IT ticket. | Already Built | HIGH
Modern Architecture | Zero-Blocking Integration Architecture | Integration Hub with manual fallback for every external connection. One API failure never blocks core ops. | IntelliDealer integrations (VitalEngage SMS, etc.) are tightly coupled — failures cascade. | Uptime insulation. No "the system is down, can't take your order." | Phase 1 Sprint 1 | HIGH
Modern Architecture | Data Ownership & Portability | Nightly backups to OneDrive + Dropbox + Cloudflare R2 owned by QEP. No vendor lock-in. | IntelliDealer data lives in VitalEdge's database. QEP pays ongoing license to access own data. | QEP's data is QEP's. No ransom scenarios. | Phase 1 Sprint 1 | STRATEGIC
Modern Architecture | Anthropic Claude API (Data Not Used for Training) | Every AI feature uses Claude. Data is never used for model training. | IntelliDealer has no AI. | Compliance-safe AI. Customer PII never leaves Anthropic's boundary. | Already Built | HIGH
Integration Surface | Microsoft Graph API (Outlook/OneDrive/Teams) | Native two-way sync with QEP's M365 — email, calendar, OneDrive docs, Teams chat, SharePoint. | IntelliDealer has no M365 integration. Dual data entry today. | Every email and doc auto-linked to the right customer/deal. | Phase 1 Sprint 4 | HIGH
Integration Surface | Twilio SMS | Modern, branded SMS with delivery receipts, opt-out compliance, and AI response drafting. | VitalEngage in IntelliDealer is limited and tied to IntelliDealer's billing. | Cheaper, better, and QEP-controlled. | Phase 1 Sprint 4 | MEDIUM
Integration Surface | 8x8 Call Integration | Phone system fully integrated — every call logged, transcribed, and summarized into the CRM. | IntelliDealer has no phone integration. | Historical call context on every customer record. | Phase 1 Sprint 4 | HIGH
Integration Surface | QuickBooks Online API | Modern cloud QB integration for AR/AP/GL export. | IntelliDealer posts to QB via batch export today. | Real-time financial truth. No month-end reconciliation nightmares. | Phase 8 | HIGH
Integration Surface | ADP Payroll API | Direct payroll sync — employee master, time tracking, commissions flow to ADP. | IntelliDealer has no ADP integration. Manual export today. | Commissions and pay are automatic. | Phase 8/9 | MEDIUM
Integration Surface | OEM Portal SSO Dashboard | One login for all 22+ OEM portals (Bandit, Develon, Yanmar, etc.). Unified catalog, bulletins, build sheets. | IntelliDealer does not aggregate OEM portals. Separate logins today. | Eliminates the #1 daily frustration for parts and sales staff. | Phase 9 | STRATEGIC
Integration Surface | ElevenLabs Voice | High-quality AI voice for customer callbacks, appointment reminders, voice responses. | Does not exist. | Scale customer communication without hiring. | Phase 9 | LOW
CRM / Workflow | Company-First Hierarchy | Parent/child company relationships. Contacts nest under companies. Equipment nests under companies AND deals. | IntelliDealer Customer Profile is flat — no parent/subsidiary modeling. | One record for Reliable Services with all 12 locations nested. No more duplicate customer numbers. | Phase 1 Sprint 2 | HIGH
CRM / Workflow | Smart Duplicate Detection & Merge | ML-based duplicate detection on company/contact creation. Suggests merges with full preview. | IntelliDealer has no dedup. QEP currently has thousands of duplicates per HubSpot. | Clean data from day one. No more "which Bob Smith is the real one?" | Phase 1 Sprint 2 | HIGH
CRM / Workflow | Kanban Visual Pipeline | Drag-drop deal cards across pipeline stages. Equipment-aware cards showing machine, price, days-in-stage. | IntelliDealer Prospect Board is list-based and static. | Ryan ("visual guy") can finally see the pipeline the way he thinks. | Phase 1 Sprint 3 | HIGH
CRM / Workflow | Custom Fields (Per Entity) | Add custom fields to companies, contacts, equipment, deals without IT ticket. | IntelliDealer custom fields require vendor assistance. | QEP evolves the platform without waiting on BlackRock or VitalEdge. | Phase 1 Sprint 2 | MEDIUM
CRM / Workflow | Follow-Up Automation | Rules-based and AI-suggested follow-ups. Auto-create tasks when deals hit certain conditions. | Manual follow-ups only in IntelliDealer. | Nothing falls through the cracks. | Phase 1 Sprint 3 | HIGH
CRM / Workflow | Real-Time Live Dashboards | Stats cards, charts, pipeline views update in real time as data changes. | IntelliDealer reporting is batch or on-demand refresh. | Ryan opens his phone Sunday morning and sees current week-to-date. | Already Built | HIGH
Security & Admin | Row-Level Security (RLS) | Permissions enforced at database level via Supabase RLS. UI hides fields; RLS is the real gate. | IntelliDealer uses "Security Switches" — UI-layer permissions only. | Even if someone bypasses the UI, they cannot read data they shouldn't. | Phase 1 Sprint 1 | HIGH
Security & Admin | Granular Role Matrix | 9 distinct roles (owner, manager, admin, sales_rep, service_writer, parts_counter, technician, finance_admin). Margin data locked from sales reps. | IntelliDealer permission model is coarser and less enforceable. | Sales reps see their deals without seeing margin. Finance sees all. | Phase 1 Sprint 1 | HIGH
Security & Admin | Admin Integration Hub | Central UI for managing all external integrations — API keys, sync status, error logs, manual fallback toggles. | IntelliDealer has no integration hub. | Rylee/Ryan can see integration health without a BlackRock support ticket. | Phase 1 Sprint 1 | HIGH
Security & Admin | Full Audit Log | Every data change logged: who, when, what changed, old value, new value. | IntelliDealer audit logs exist but are limited and not easily queried. | Compliance, dispute resolution, training. | Phase 1 Sprint 1 | MEDIUM
Customer-Facing | External Customer Portal | Customers log in to see their equipment, service history, open work orders, invoices, and submit service requests. | IntelliDealer has a Customer Portal PDF but adoption is limited. QEP's will be AI-enhanced. | Customers self-serve. Phone volume drops. | Phase 9 | HIGH
Customer-Facing | Branded SMS & Email | Every customer touchpoint uses QEP branding, fonts, signature block. Tone-matched to Rylee's voice (not AI-sounding). | Generic IntelliDealer/VitalEngage templates. | QEP looks like a premium operation. | Phase 1 Sprint 4 | MEDIUM
Analytics & BI | Win/Loss Analysis with Reasons | Every closed deal captures why it won or lost. Patterns surface automatically. | IntelliDealer has close dates but no structured win/loss reason analysis. | Stop losing to Yancey without knowing why. | Phase 2 | HIGH
Analytics & BI | Rep Performance Scorecards | Individual dashboards for each rep — quota, pipeline, activities, win rate, average deal size. | IntelliDealer commission reports only, not forward-looking performance views. | Coaching is data-driven. | Phase 2 | HIGH
Analytics & BI | Territory Optimization | Analyze territory coverage, identify underserved accounts, suggest reassignment. | Does not exist in IntelliDealer. | Maximize rep productivity. | Phase 5 | MEDIUM
Analytics & BI | Predictive Alerts | AI flags customers at risk of churning, deals at risk of stalling, equipment at risk of warranty expiration without renewal. | Does not exist. | Proactive, not reactive. | Phase 5 | HIGH
Process | Nightly Multi-Target Backup | Nightly dump to OneDrive + Dropbox + Cloudflare R2. 3 independent copies. | IntelliDealer backup is single-vendor (VitalEdge). | Disaster recovery without vendor dependency. | Phase 1 Sprint 1 | HIGH
Process | Dev/Staging/Production Environments | Full environment separation. Changes tested in staging before production deploy. | IntelliDealer updates roll directly to production via vendor releases. | No more surprise regressions during business hours. | Phase 1 | HIGH
Process | 15-Agent Paperclip Build Pipeline | Architect → Engineer → QA → DevOps → Security pipeline for every feature. Full audit trail. | N/A — vendor build model. | QEP OS evolves continuously instead of waiting for vendor release cycles. | Already Built | STRATEGIC

## Phase Summary
Phase | Features Documented | Total Screenshots | PDFs | Status Mix
Phase 1 — Core CRM | 7 | 10 | 3 | IN BUILD (Sprint 2)=5; IN BUILD (Sprint 3)=1; PLANNED (Phase 9)=1
Phase 2 — Sales Intelligence | 7 | 43 | 5 | BUILT — NEEDS PARITY=1; PLANNED (Phase 2)=5; PLANNED (Phase 8)=1
Phase 3 — Parts Department | 7 | 23 | 5 | PLANNED (Phase 3)=5; PLANNED (Phase 3/4)=2
Phase 4 — Service Department | 18 | 29 | 8 | PLANNED (Phase 4)=18
Phase 5 — Deal Genome (BI) | 4 | 9 | 1 | IN PARALLEL BUILD (Phase 5)=4
Phase 6 — Rental Fleet | 1 | 0 | 1 | PLANNED (Phase 6)=1
Phase 8 — Financial Operations | 11 | 16 | 7 | PLANNED (Phase 8)=9; PLANNED (Phase 8/9)=2
Phase 9 — Advanced Intelligence | 1 | 0 | 1 | PLANNED (Phase 9)=1
Cross-Cutting | 2 | 3 | 2 | GAP — SCOPE CHECK=1; PLANNED (Phase 8/9)=1

## Coverage Legend
Status | Meaning
BUILT | Already working in QEP OS staging
BUILT — NEEDS PARITY | Built in QEP but must match IntelliDealer feature set
PARTIAL | Partial coverage in QEP — gaps remain
IN BUILD | Currently in Phase 1 active sprint work
IN PARALLEL BUILD (Phase 5) | Deal Genome engine build running alongside Phase 1
PLANNED (Phase N) | Scheduled for future QEP phase
GAP — SCOPE CHECK | Not in current roadmap — needs decision whether to include
REVIEW | Ambiguous — manual review required

## Advantages Summary
Category | Count | Strategic | High | Medium | Low
AI-Native | 10 | 2 | 5 | 3 | 0
Modern Architecture | 7 | 1 | 5 | 1 | 0
Integration Surface | 7 | 1 | 3 | 2 | 1
CRM / Workflow | 6 | 0 | 5 | 1 | 0
Security & Admin | 4 | 0 | 3 | 1 | 0
Customer-Facing | 2 | 0 | 1 | 1 | 0
Analytics & BI | 4 | 0 | 3 | 1 | 0
Process | 3 | 1 | 2 | 0 | 0
TOTAL | 43 | 5 | 27 | 10 | 1